## Slide 1: One ITS
Project Charter
06/15/2015
Enterprise Applications Services
Research IT
Enterprise Infrastructure Services
Client Services and Support
OCIO
Inf. Security
Inf. Security

## Slide 2: Why - Market
Pace of change in Higher Education business models
  driven by economic and technological advances
  fundamental economic principle of supply and demand
Create 3 Areas of Focus:
  “inflection point” - trends that have dominated thought leadership & early adopters are now mainstream.
  “technical problems to business problems” - the ensuing interdependence
  "new normal”
“technical to business” - fundamental reason for the organizational change
  Applications staff not organized in relation to the business, focus is perpetually diluted
Top 10 IT Issues, 2015: Inflection Point by Susan Grajek Published on Monday, January 12, 2015

## Slide 3: Why – UAlbany!
A University reaching for the world with 4 “stakes” ambitiously in the ground, requires an IT Applications unit that has people organized to be:
    Engaging and Collaborative
    Entrepreneurial and Service-Oriented
    Disciplined and flexible
    Compact and Accountable
    Steady and Effective leaders of efficient and effective applications services
Annual Address to the Faculty by President Robert Jones Published on Tuesday, April 22, 2014

## Slide 4: Project Overview – Your input!
Driven from the ITS feedback on the concept and 7 driving principles… Available on the Wiki for reference
https://wiki.albany.edu/display/OCIO/All+Staff+Meetings

## Slide 5: Project Overview – Goals
Streamlined Goals
  One ITS principles are time and technology transcendent
  Ensured through the use of industry standard disciplines to ensure:
    We communicate, often and honestly, across the University
    There are only University priorities, and we work together to balance them
    We seek out information and use it to break down silos, wherever they are
    We hold ourselves and one another accountable
    We use a common set of tools, procedures and practices
1
2
3
4
5

## Slide 6: Project Overview – Objectives
Implement standard administrative items that Symbolize One ITS
  if we cannot do these, we cannot do anything else
Implement a Project & Portfolio Management process that is engaging, disciplined, and transparent
  Informed by the Project Management Institute PM Body of Knowledge (PMBOK)
Implement Service Management process that is customer engaging, disciplined, and transparent
  Informed by the Information Technology Infrastructure Library
Implement foundational Enterprise Architecture materials and processes that include the current and future states for road-mapping and budgeting optimization
  Informed by enterprise architecture disciplines of business, information, and technical modeling
5
1
3
4
5
Coverage
1
2
3
4
5
1
2
3
4
1
3
4
5

## Slide 7: Project Overview – Scope Summary
  4 Parallel Paths of Work – each one informing the other
    Symbols *
    Project and Portfolio Management *
    Service Management
    Enterprise Architecture
*Start first…
Notes: ----- Meeting Notes (10/9/14 12:10) -----
Not going to wait to start the other 2...

## Slide 8: Project Overview – Scope Summary
In Scope
  Each path will:
    Define Current State process, people, and technology
      Define Immediate fixes/implementations
    Evaluate alternatives (peers, market)
    Propose Desired State process, people, and technology
    Implement short-term and plan long-term
Out of scope
  Sweeping organizational and/or financial changes
  Completed implementation – long-term implementation

## Slide 9: Project Overview – CSFs and Risks
Critical Success Factors
  Cabinet Buy-in to Oneness
  Manager / Leader / Team Member Buy-in to Oneness
  Enable:
    Service Based and Campus Budgeting
    IT Governance
  University at Albany is what we are here for…
    Will our service consumers engage in this willingly?
      Would You?
High Level Risks
  Customer reaction to process standardization
  Facing the unknown together
Pinky Swear!
Communication
Stay Together

## Slide 10: Change Acknowledgement
This will impact the way you work in a positive manner…
We all need to be positive change agents
Overt, Healthy Dialogue is the Way!!!
That starts now…

## Slide 11: Project Overview – Assumptions
Assumptions
  Overall FTE Count not increasing (positions to fill)
  Budget not increasing
  Technology and new service offerings available to be leveraged
  ITS enthusiasm for U Albany will ensure positive change
    Desire to do a good job!
Constraints
  Staff engagement and schedule – think/work differently
  General disbelief in ability to get this done!

## Slide 12
Enterprise Architecture & Symbols
Service Delivery
CHANGE & RELEASE MANAGEMENT
Service Support
CAPTURE
ALL
DEMAND
ServiceDown?
Project & Portfolio Management
Work Portfolio
Proposed Projects
Active Projects
Operations
SELECTION
ALIGN THE
PORTFOLIO
MANAGE STRATEGIC CHANGE
Departmental Strategic Plan
Roadmap
SR / Proj?
SR
INCIDENT MGMT
Change Roster & Configuration Management DB
No
Yes
Project
Problem?
Yes
Service Catalogue
End
No
BUSINESS VALUE & STRATEGIC PLANNNIG
DEPLOYMENT
Communication
Training
KPI Reporting
Satisfaction Surveys
Resource Portfolio
Availability
Allocation
Effort
EFFORT REPORTING
INITIATION
PLANNING
EXECUTION
Parallel Output
PROBLEM MGMT
BUSINESS VALUE & STRATEGIC PLANNNIG
Project Scope Concept – Path Overlay

## Slide 13: Legend
Shape | Description
 | Input accumulator
 | Decision step
 | Process output and input connector
 | Macro – process start and end
 | Process – a set of activities logically grouped
 | Information used as output or input to a process.

## Slide 14: Project Organization
Cross Departmental Team
Approve
Manage
Propose
Consult